## Sheet1
Project | Start Date | Status | Cost | Code | Task Name | End Date | Division Budget
Assigned To: Al Bines
Public Website | 2014-05-04 | On-Hold | 300 | 06 | Purchase additional software licenses, if needed | 2014-05-27 | 1000
Migrate from SQL Server | 2014-06-26 | Pending | 0 | 05 | Decommission SQL Server | 2014-09-23 | 500
Maintain Support Systems | 2014-05-14 | Open | 300 | 1c | Arrange for vacation coverage | 2014-06-06 | 500
600
Assigned To: Hank Davis
Discussion Forum | 2014-05-13 | Closed | 250 | 09 | Identify owners | 2014-05-16 | 300
Discussion Forum | 2014-05-22 | Open | 450 | 08 | Monitor participation | 2014-05-30 | 500
Discussion Forum | 2014-05-21 | Closed | 100 | 05 | Install APEX application on internet server | 2014-05-21 | 100
800
Assigned To: Irene Jones
Employee Satisfaction Survey | 2014-05-12 | On-Hold | 1200 | 06 | Complete questionnaire | 2014-05-26 | 800
Employee Satisfaction Survey | 2014-06-03 | On-Hold | 200 | 07 | Review with legal | 2014-06-09 | 400
Employee Satisfaction Survey | 2014-06-10 | On-Hold | 0 | 10 | Plan rollout schedule | 2014-06-18 | 750
1400
Assigned To: James Cassidy
Migrate from SQL Server | 2014-05-28 | Pending | 0 | 15 | Obtain SQL Server credentials | 2014-05-31 | 500
APEX Environment Configuration | 2014-04-05 | Closed | 100 | 1f | Run installation | 2014-04-05 | 100
APEX Environment Configuration | 2014-03-27 | Closed | 100 | 04 | Determine Web listener configuration(s) | 2014-03-27 | 100
Train Developers in APEX | 2014-04-25 | Closed | 500 | 07 | Create training workspace | 2014-05-02 | 700
APEX Environment Configuration | 2014-03-28 | Closed | 200 | 1.12 | Select servers for Development, Test, Production | 2014-04-02 | 600
900
Assigned To: John Watson
Train Developers in APEX | 2014-04-25 | Closed | 100 | 0e | Publish links to self-study courses | 2014-04-25 | 100
Train Developers in APEX | 2014-04-22 | On-Hold | 1000 | 05 | Publish development standards | 2014-06-28 | 2000
APEX Environment Configuration | 2014-04-04 | Closed | 100 | 06 | Create pilot workspace | 2014-04-04 | 100
APEX Environment Configuration | 2014-04-04 | Closed | 200 | 1c | Configure Workspace provisioning | 2014-04-04 | 100
APEX Environment Configuration | 2014-03-28 | Closed | 200 | 09 | Specify security authentication scheme(s) | 2014-03-30 | 300
APEX Environment Configuration | 2014-03-26 | Closed | 100 | 05 | Identify server requirements | 2014-03-27 | 200
Load Packaged Applications | 2014-05-02 | Open | 1500 | 0b | Customize solutions | 2014-07-25 | 4000
Migrate from SQL Server | 2014-07-20 | Pending | 0 | 09 | Import data | 2014-08-16 | 1000
Migrate from SQL Server | 2014-07-19 | Pending | 0 | 08 | Migrate table structures | 2014-08-13 | 2500
Load Packaged Applications | 2014-06-04 | Pending | 0 | 09 | Train developers / users | 2014-08-18 | 8000
Migrate Access Application | 2014-05-22 | Open | 0 | 0a | End-user Training | 2014-07-17 | 2000
Load Packaged Applications | 2014-05-21 | Open | 200 | 07 | Implement in Production | 2014-07-29 | 1500
Load Packaged Applications | 2014-05-01 | Closed | 100 | 09 | Install in development | 2014-05-01 | 100
Load Packaged Applications | 2014-04-27 | Closed | 200 | 15 | Identify point solutions required | 2014-04-29 | 300
3700
Assigned To: Mark Nile
Migrate Access Application | 2014-05-11 | Closed | 500 | 04 | Migrate pilot applications to APEX | 2014-05-16 | 500
Migrate Access Application | 2014-05-18 | Closed | 100 | 09 | Post-migration review | 2014-05-18 | 100
Email Integration | 2014-05-06 | Closed | 200 | 05 | Check software licenses | 2014-05-07 | 200
Email Integration | 2014-05-07 | Open | 2000 | 04 | Get RFPs for new server | 2014-05-28 | 1000
Migrate Access Application | 2014-05-22 | Open | 1000 | 15 | Migrate Access applications | 2014-07-15 | 8000
Migrate from SQL Server | 2014-06-14 | Pending | 0 | 06 | Map data usage | 2014-07-27 | 8000
Migrate Access Application | 2014-05-20 | Closed | 600 | 0a | Plan migration schedule | 2014-05-20 | 200
Migrate Access Application | 2014-05-26 | Open | 1500 | 07 | User acceptance testing | 2014-07-25 | 6000
Email Integration | 2014-04-02 | Closed | 3000 | 06 | Complete plan | 2014-05-08 | 1500
Migrate from SQL Server | 2014-06-28 | Pending | 0 | 04 | Implement integration using Oracle | 2014-07-28 | 1500
Migrate from SQL Server | 2014-06-02 | Pending | 0 | 0a | Identify integration points | 2014-06-22 | 2000
Migrate from SQL Server | 2014-07-30 | Pending | 0 | 05 | Notify users | 2014-08-02 | 200
Email Integration | 2014-06-06 | Pending | 0 | 04 | Purchase backup server | 2014-07-02 | 3000
Migrate Access Application | 2014-05-04 | Closed | 300 | 1d | Identify pilot Access applications | 2014-05-09 | 500
9200
Assigned To: Myra Sutcliff
Bug Tracker | 2014-04-10 | On-Hold | 2750 | 0c | Review automated testing tools | 2014-05-09 | 1500
Bug Tracker | 2014-06-14 | On-Hold | 0 | 15 | Train developers on tracking bugs | 2014-08-03 | 2000
Bug Tracker | 2014-06-26 | Pending | 0 | 1e | Measure effectiveness of improved QA | 2014-07-26 | 1500
Bug Tracker | 2014-04-09 | Closed | 100 | 0a | Implement bug tracking software | 2014-04-09 | 100
Forms Conversion | 2014-08-13 | Pending | 0 | 20 | End-user Training | 2014-10-25 | 2500
Bug Tracker | 2014-05-10 | Open | 3500 | 0b | Document quality assurance procedures | 2014-06-13 | 4000
6350
Assigned To: Pam King
Maintain Support Systems | 2014-03-26 | On-Hold | 8000 | 06 | HR software upgrades | 2014-05-21 | 7000
Software Projects Tracking | 2014-04-29 | Closed | 100 | 04 | Conduct project kickoff meeting | 2014-04-29 | 100
Convert Excel Spreadsheet | 2014-05-09 | Open | 2500 | 0b | Collect mission-critical spreadsheets | 2014-07-10 | 4000
Convert Excel Spreadsheet | 2014-05-09 | Open | 6000 | 1a | Create APEX applications from spreadsheets | 2014-10-23 | 10000
Convert Excel Spreadsheet | 2014-05-09 | Open | 1000 | 08 | Lock spreadsheets | 2014-10-23 | 800
Convert Excel Spreadsheet | 2014-05-10 | Open | 1000 | 04 | Send links to previous spreadsheet owners | 2014-10-25 | 1500
Forms Conversion | 2014-05-15 | Closed | 100 | 07 | Post-migration review | 2014-05-15 | 100
Forms Conversion | 2014-05-16 | Closed | 100 | 06 | Plan migration schedule | 2014-05-16 | 100
Forms Conversion | 2014-05-20 | Open | 300 | 04 | Migrate Oracle Forms | 2014-09-27 | 12000
Maintain Support Systems | 2014-05-23 | Open | 1700 | 0a | Investigate new Virus Protection software | 2014-06-07 | 1500
Migrate from SQL Server | 2014-06-27 | Pending | 0 | 06 | Convert processes | 2014-08-25 | 3000
Forms Conversion | 2014-10-16 | Pending | 0 | 04 | Rollout migrated Forms in APEX | 2014-10-27 | 500
20800
Assigned To: Russ Sanders
Maintain Support Systems | 2014-03-26 | On-Hold | 9500 | 12 | Apply Billing System updates | 2014-05-25 | 7000
9500
Assigned To: Russ Saunders
Forms Conversion | 2014-07-11 | Pending | 0 | 09 | User acceptance testing | 2014-10-13 | 2500
Forms Conversion | 2014-06-26 | Pending | 0 | 14 | Test migrated applications | 2014-10-18 | 6000
0
Assigned To: Scott Spencer
Forms Conversion | 2014-05-01 | Closed | 400 | 1f | Migrate pilot Forms to APEX | 2014-05-14 | 500
Forms Conversion | 2014-04-29 | Closed | 200 | 0f | Identify pilot Oracle Forms applications | 2014-04-30 | 200
Migrate from SQL Server | 2014-06-02 | Pending | 0 | 06 | Create DB Connection to Oracle | 2014-06-02 | 100
600
Assigned To: Tiger Scott
Public Website | 2014-06-04 | On-Hold | 800 | 0b | Develop web pages | 2014-07-10 | 2000
Public Website | 2014-04-30 | Closed | 200 | 0e | Determine host server | 2014-05-01 | 200
1000
Assigned To: Tom Suess
Public Website | 2014-07-12 | On-Hold | 0 | 08 | Plan rollout schedule | 2014-07-12 | 100
Software Projects Tracking | 2014-05-09 | Open | 600 | 06 | Customize Software Projects software | 2014-06-14 | 1000
Software Projects Tracking | 2014-05-04 | Closed | 200 | 1f | Enter base data (Projects, Milestones, etc.) | 2014-05-05 | 200
Public Website | 2014-05-01 | Closed | 100 | 04 | Check software licenses | 2014-05-01 | 100
Software Projects Tracking | 2014-05-06 | Closed | 400 | 0a | Load current tasks and enhancements | 2014-05-10 | 500
1300